## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | 1 | Collect unstructured,semi structured and structured datasets. |  |  |  | 3- Completed
1 | 1 | 2 | Data Ingestion has been done on collected data and has been converted to JSON format.Missing values has also been handled. |  | 1 |  | 3- Completed
1 | 1 | 3 | Ingested Data has been Normalized like removing stop words,emojis,punctuation and converted to standard format. |  | 1 |  | 3- Completed
2 | 2 | 4 | Named Entity Recognition has been done on the normalized file. |  | 1 |  | 3- Completed
2 | 2 | 5 | Found relationships between the enities and created triples using the relationships. |  | 2 |  | 3- Completed
2 | 2 | 6 | Built knowledge graph in Neo4j database using triples created. |  | 2 |  | 3- Completed
3 | 3 | 7 | For ingested data stored in json format, embeddings and metadata has been created |  | 1 |  | 3- Completed
3 | 3 | 8 | Embeddings has been stored in FAISS vector database |  | 3 |  | 3- Completed
3 | 3 | 9 | Created Hybrid RAG pipeline by retriving data from vector database and knowledge graph |  | 2,3 |  | 3- Completed
4 | 4 | 10 | Evaluated the model by giving score for how well the retrived chunks match the question and answer. |  | 2,3 |  | 3- Completed
4 | 4 | 11 | Created UI for the Enterprise Chatbot using Streamlit |  | 3,4 |  | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
| 1 | Data collection of structured,unstructured and semi structure. Ingest collected and handel missing values | 2025-12-08 | 2025-12-14 |  | Data Collection | Completed | 4
| 2 | Normalzation of ingested data and making it to standard form | 2025-12-15 | 2025-12-21 |  | Code | Completed | 6
SPRINT 2 BACKLOG
| 3 | Named Entity Recognition of normalized data | 2025-12-22 | 2025-12-28 |  | Code | Completed | 2
| 4 | Formation of relationship and Triples and storing it in Neo4j Database | 2025-12-29 | 2026-01-04 |  | Code | Completed | 5
SPRINT 3 BACKLOG
| 5 | Creation of embeddings and metadata | 2026-01-05 | 2026-01-11 |  | Code | Completed | 7
| 6 | Store embeddings in FAISS vector database | 2026-01-12 | 2026-01-18 |  | Code | Completed | 3
SPRINT 4 BACKLOG
| 7 | Hybrid RAG generation by combining semantic search retrival from FAISS vector database and knowledge graph | 2026-01-19 | 2026-01-25 |  | Code | Completed | 10
| 8 | Create UI for Enterprise Chatbot and integrated with hybrid RAG system | 2026-01-26 | 2026-01-31 |  | Design | Completed | 8
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 8th Dec | Guidelines for data collection and initial model architecture. | Collected unstructured, semi-structured, and structured datasets. Performed Data Ingestion and converted all sources to JSON format.
1 | 15th Dec | Handling inconsistencies in raw text data | Performed Data Cleaning (missing values), Normalization (removing stop words, emojis, punctuation)
2 | 22nd Dec | Preparing for entity extraction. | executed Named Entity Recognition (NER).
2 | 29th Dec | Mapping complex relationships between extracted entities for the Knowledge Graph. | Identified entity relationships and generated triples. Successfully built and migrated the Knowledge Graph into the Neo4j database.
3 | 5th Jan | Integrating disparate retrieval systems (Vector vs. Graph). | Generated Embeddings and Metadata for JSON data and stored them in FAISS. Developed the Hybrid RAG pipeline to query both FAISS and Neo4j simultaneously.
4 | 19th Jan | Closing the loop on model evaluation and finalizing the user interface. | Conducted RAG Evaluation (scoring chunk-to-query relevancy). Developed and refined the Streamlit UI for the final Enterprise Chatbot deployment.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 8th Dec | 21st Dec |  | Data Collection and Preprocessing
2 | 2 | 22nd Dec | 4th Jan |  | Knowledge Graph generation
3 | 3 | 5th Jan | 18th Jan |  | Hybrid Rag model
4 | 4 | 19th Jan | 31st Jan |  | Building dashboard for entrprise chatbot
5
6
7